## README
AMERICAN FUSION INC. — 90-DAY EDITORIAL CALENDAR
Deliverable 02 of the Day-14 Foundation Package
Prepared by BotMakers Inc. · Version 1.0
HOW TO USE THIS WORKBOOK
This workbook contains the full 90-day publishing plan across all six channels.
Tabs:
• Master Calendar — day-by-day plan, every post on every channel, with owner, pillar, status
• LinkedIn Company — filtered view of the company LinkedIn cadence (5 posts/wk)
• Executive Posts — filtered view of Nelson / Reid / Hawkins ghost-written cadence
• X / Twitter — filtered view of X cadence (7–14 posts/wk)
• YouTube & Newsletter — long-form publishing cadence
• Instagram — visual cadence (3 posts/wk)
• Content Pillars — the six content pillars every post must map to
CONVENTIONS
• Pillar codes: BIP=Build in Public, EDU=Education, AI=AI Energy, DEF=Defense, IR=Investor Relations, FV=Founder Voice
• Status: PLANNED → DRAFTED → REVIEWED → APPROVED → SCHEDULED → PUBLISHED
• Owner: BM=BotMakers drafts; AMFN=AMFN approves; LEGAL=securities counsel review required
• Every post requires LEGAL review if it touches material milestones, financial guidance, or partnership disclosures (Reg FD)
CADENCE SUMMARY (PER WEEK)
LinkedIn Company: 5 posts/week (~20/month, ~65/quarter)
LinkedIn — Nelson: 3 posts/week (~12/month, ~36/quarter)
LinkedIn — Reid: 2 posts/week (~8/month, ~24/quarter)
LinkedIn — Hawkins: 2 posts/week (~8/month, ~24/quarter)
X / Twitter: 10 posts/week (~40/month, ~120/quarter)
Instagram: 3 posts/week (~12/month, ~36/quarter)
YouTube: 2 videos/month
Newsletter: 2 sends/month
─────────────────────────────────────
TOTAL CONTENT PIECES: ~340 across the 90-day Foundation phase

## Content Pillars
Code | Pillar | Description | Primary Owner
BIP | Build in Public | Texatron 5 MW unit progress. Welds, diagnostics, engineering decisions, the lab, the team. Photographic and specific. | Nelson + BotMakers
EDU | Education & Thought Leadership | What is aneutronic fusion? Why D–He-3? How does direct energy conversion work? Search-visible, evergreen, category-defining. | Nelson + BotMakers
AI | AI Energy Narrative | Anchored to IEA data and hyperscaler capex. AMFN POV on the AI power crisis and why aneutronic is best-positioned. | Nelson + Hawkins
DEF | Defense & National Security | EO 14299, ANPI, Janus, Project Pele context. AMFN as the second-cohort aneutronic answer. Reid voice leads. | Reid
IR | Investor Relations | Milestone announcements, financial transparency, OTCQB and Frankfurt progress, fuel supply chain updates. | Hawkins (LEGAL review required)
FV | Founder Voice | Nelson on technical philosophy. Hawkins on capital strategy. Reid on procurement. Each in a defined lane. | All three executives

## Master Calendar
Day | Date | Day of Week | Channel | Owner | Pillar | Working Title / Hook | Status | Notes
1 | 2026-06-15 | Monday | LinkedIn Company | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
1 | 2026-06-15 | Monday | LinkedIn — Nelson | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
1 | 2026-06-15 | Monday | X / Twitter | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
1 | 2026-06-15 | Monday | X / Twitter | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
1 | 2026-06-15 | Monday | Instagram | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
1 | 2026-06-15 | Monday | Newsletter | BM | IR/DEF | Bi-monthly send: State of Fusion + Reid Procurement Note + Texatron progress | PLANNED | LEGAL review on any milestone references
2 | 2026-06-16 | Tuesday | LinkedIn — Reid | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
2 | 2026-06-16 | Tuesday | X / Twitter | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
2 | 2026-06-16 | Tuesday | X / Twitter | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
3 | 2026-06-17 | Wednesday | LinkedIn Company | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
3 | 2026-06-17 | Wednesday | LinkedIn — Nelson | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
3 | 2026-06-17 | Wednesday | X / Twitter | BM | AI | Hyperscaler capex commentary | PLANNED
3 | 2026-06-17 | Wednesday | X / Twitter | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
3 | 2026-06-17 | Wednesday | Instagram | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
4 | 2026-06-18 | Thursday | LinkedIn Company | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
4 | 2026-06-18 | Thursday | LinkedIn — Hawkins | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
4 | 2026-06-18 | Thursday | X / Twitter | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
4 | 2026-06-18 | Thursday | X / Twitter | BM | EDU | What is helium-3? Where does it come from? | PLANNED
5 | 2026-06-19 | Friday | LinkedIn Company | BM | FV | Friday: a single sharp thought from the team | PLANNED
5 | 2026-06-19 | Friday | LinkedIn — Nelson | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
5 | 2026-06-19 | Friday | X / Twitter | BM | BIP | Photo + caption: shop floor / control room | PLANNED
5 | 2026-06-19 | Friday | X / Twitter | BM | EDU | Friday fusion fact | PLANNED
5 | 2026-06-19 | Friday | Instagram | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
6 | 2026-06-20 | Saturday | X / Twitter | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
8 | 2026-06-22 | Monday | LinkedIn Company | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
8 | 2026-06-22 | Monday | LinkedIn — Nelson | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
8 | 2026-06-22 | Monday | X / Twitter | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
8 | 2026-06-22 | Monday | X / Twitter | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
8 | 2026-06-22 | Monday | Instagram | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
9 | 2026-06-23 | Tuesday | LinkedIn — Reid | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
9 | 2026-06-23 | Tuesday | X / Twitter | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
9 | 2026-06-23 | Tuesday | X / Twitter | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
10 | 2026-06-24 | Wednesday | LinkedIn Company | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
10 | 2026-06-24 | Wednesday | LinkedIn — Nelson | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
10 | 2026-06-24 | Wednesday | X / Twitter | BM | AI | Hyperscaler capex commentary | PLANNED
10 | 2026-06-24 | Wednesday | X / Twitter | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
10 | 2026-06-24 | Wednesday | Instagram | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
10 | 2026-06-24 | Wednesday | YouTube | BM/Nelson | BIP/EDU | Technology Deep-Dive — aneutronic fundamentals series | PLANNED
11 | 2026-06-25 | Thursday | LinkedIn Company | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
11 | 2026-06-25 | Thursday | LinkedIn — Hawkins | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
11 | 2026-06-25 | Thursday | X / Twitter | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
11 | 2026-06-25 | Thursday | X / Twitter | BM | EDU | What is helium-3? Where does it come from? | PLANNED
12 | 2026-06-26 | Friday | LinkedIn Company | BM | FV | Friday: a single sharp thought from the team | PLANNED
12 | 2026-06-26 | Friday | LinkedIn — Nelson | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
12 | 2026-06-26 | Friday | X / Twitter | BM | BIP | Photo + caption: shop floor / control room | PLANNED
12 | 2026-06-26 | Friday | X / Twitter | BM | EDU | Friday fusion fact | PLANNED
12 | 2026-06-26 | Friday | Instagram | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
13 | 2026-06-27 | Saturday | X / Twitter | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
15 | 2026-06-29 | Monday | LinkedIn Company | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
15 | 2026-06-29 | Monday | LinkedIn — Nelson | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
15 | 2026-06-29 | Monday | X / Twitter | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
15 | 2026-06-29 | Monday | X / Twitter | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
15 | 2026-06-29 | Monday | Instagram | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
16 | 2026-06-30 | Tuesday | LinkedIn — Reid | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
16 | 2026-06-30 | Tuesday | X / Twitter | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
16 | 2026-06-30 | Tuesday | X / Twitter | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
17 | 2026-07-01 | Wednesday | LinkedIn Company | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
17 | 2026-07-01 | Wednesday | LinkedIn — Nelson | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
17 | 2026-07-01 | Wednesday | X / Twitter | BM | AI | Hyperscaler capex commentary | PLANNED
17 | 2026-07-01 | Wednesday | X / Twitter | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
17 | 2026-07-01 | Wednesday | Instagram | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
17 | 2026-07-01 | Wednesday | Newsletter | BM | IR/DEF | Bi-monthly send: State of Fusion + Reid Procurement Note + Texatron progress | PLANNED | LEGAL review on any milestone references
18 | 2026-07-02 | Thursday | LinkedIn Company | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
18 | 2026-07-02 | Thursday | LinkedIn — Hawkins | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
18 | 2026-07-02 | Thursday | X / Twitter | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
18 | 2026-07-02 | Thursday | X / Twitter | BM | EDU | What is helium-3? Where does it come from? | PLANNED
19 | 2026-07-03 | Friday | LinkedIn Company | BM | FV | Friday: a single sharp thought from the team | PLANNED
19 | 2026-07-03 | Friday | LinkedIn — Nelson | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
19 | 2026-07-03 | Friday | X / Twitter | BM | BIP | Photo + caption: shop floor / control room | PLANNED
19 | 2026-07-03 | Friday | X / Twitter | BM | EDU | Friday fusion fact | PLANNED
19 | 2026-07-03 | Friday | Instagram | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
20 | 2026-07-04 | Saturday | X / Twitter | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
22 | 2026-07-06 | Monday | LinkedIn Company | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
22 | 2026-07-06 | Monday | LinkedIn — Nelson | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
22 | 2026-07-06 | Monday | X / Twitter | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
22 | 2026-07-06 | Monday | X / Twitter | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
22 | 2026-07-06 | Monday | Instagram | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
23 | 2026-07-07 | Tuesday | LinkedIn — Reid | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
23 | 2026-07-07 | Tuesday | X / Twitter | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
23 | 2026-07-07 | Tuesday | X / Twitter | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
24 | 2026-07-08 | Wednesday | LinkedIn Company | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
24 | 2026-07-08 | Wednesday | LinkedIn — Nelson | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
24 | 2026-07-08 | Wednesday | X / Twitter | BM | AI | Hyperscaler capex commentary | PLANNED
24 | 2026-07-08 | Wednesday | X / Twitter | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
24 | 2026-07-08 | Wednesday | Instagram | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
24 | 2026-07-08 | Wednesday | YouTube | BM/Nelson | BIP/EDU | CEO Update — what we shipped this month | PLANNED
25 | 2026-07-09 | Thursday | LinkedIn Company | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
25 | 2026-07-09 | Thursday | LinkedIn — Hawkins | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
25 | 2026-07-09 | Thursday | X / Twitter | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
25 | 2026-07-09 | Thursday | X / Twitter | BM | EDU | What is helium-3? Where does it come from? | PLANNED
26 | 2026-07-10 | Friday | LinkedIn Company | BM | FV | Friday: a single sharp thought from the team | PLANNED
26 | 2026-07-10 | Friday | LinkedIn — Nelson | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
26 | 2026-07-10 | Friday | X / Twitter | BM | BIP | Photo + caption: shop floor / control room | PLANNED
26 | 2026-07-10 | Friday | X / Twitter | BM | EDU | Friday fusion fact | PLANNED
26 | 2026-07-10 | Friday | Instagram | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
27 | 2026-07-11 | Saturday | X / Twitter | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
29 | 2026-07-13 | Monday | LinkedIn Company | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
29 | 2026-07-13 | Monday | LinkedIn — Nelson | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
29 | 2026-07-13 | Monday | X / Twitter | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
29 | 2026-07-13 | Monday | X / Twitter | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
29 | 2026-07-13 | Monday | Instagram | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
30 | 2026-07-14 | Tuesday | LinkedIn — Reid | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
30 | 2026-07-14 | Tuesday | X / Twitter | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
30 | 2026-07-14 | Tuesday | X / Twitter | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
31 | 2026-07-15 | Wednesday | LinkedIn Company | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
31 | 2026-07-15 | Wednesday | LinkedIn — Nelson | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
31 | 2026-07-15 | Wednesday | X / Twitter | BM | AI | Hyperscaler capex commentary | PLANNED
31 | 2026-07-15 | Wednesday | X / Twitter | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
31 | 2026-07-15 | Wednesday | Instagram | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
31 | 2026-07-15 | Wednesday | Newsletter | BM | IR/DEF | Bi-monthly send: State of Fusion + Reid Procurement Note + Texatron progress | PLANNED | LEGAL review on any milestone references
32 | 2026-07-16 | Thursday | LinkedIn Company | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
32 | 2026-07-16 | Thursday | LinkedIn — Hawkins | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
32 | 2026-07-16 | Thursday | X / Twitter | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
32 | 2026-07-16 | Thursday | X / Twitter | BM | EDU | What is helium-3? Where does it come from? | PLANNED
33 | 2026-07-17 | Friday | LinkedIn Company | BM | FV | Friday: a single sharp thought from the team | PLANNED
33 | 2026-07-17 | Friday | LinkedIn — Nelson | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
33 | 2026-07-17 | Friday | X / Twitter | BM | BIP | Photo + caption: shop floor / control room | PLANNED
33 | 2026-07-17 | Friday | X / Twitter | BM | EDU | Friday fusion fact | PLANNED
33 | 2026-07-17 | Friday | Instagram | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
34 | 2026-07-18 | Saturday | X / Twitter | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
36 | 2026-07-20 | Monday | LinkedIn Company | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
36 | 2026-07-20 | Monday | LinkedIn — Nelson | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
36 | 2026-07-20 | Monday | X / Twitter | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
36 | 2026-07-20 | Monday | X / Twitter | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
36 | 2026-07-20 | Monday | Instagram | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
37 | 2026-07-21 | Tuesday | LinkedIn — Reid | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
37 | 2026-07-21 | Tuesday | X / Twitter | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
37 | 2026-07-21 | Tuesday | X / Twitter | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
38 | 2026-07-22 | Wednesday | LinkedIn Company | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
38 | 2026-07-22 | Wednesday | LinkedIn — Nelson | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
38 | 2026-07-22 | Wednesday | X / Twitter | BM | AI | Hyperscaler capex commentary | PLANNED
38 | 2026-07-22 | Wednesday | X / Twitter | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
38 | 2026-07-22 | Wednesday | Instagram | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
38 | 2026-07-22 | Wednesday | YouTube | BM/Nelson | BIP/EDU | Technology Deep-Dive — aneutronic fundamentals series | PLANNED
39 | 2026-07-23 | Thursday | LinkedIn Company | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
39 | 2026-07-23 | Thursday | LinkedIn — Hawkins | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
39 | 2026-07-23 | Thursday | X / Twitter | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
39 | 2026-07-23 | Thursday | X / Twitter | BM | EDU | What is helium-3? Where does it come from? | PLANNED
40 | 2026-07-24 | Friday | LinkedIn Company | BM | FV | Friday: a single sharp thought from the team | PLANNED
40 | 2026-07-24 | Friday | LinkedIn — Nelson | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
40 | 2026-07-24 | Friday | X / Twitter | BM | BIP | Photo + caption: shop floor / control room | PLANNED
40 | 2026-07-24 | Friday | X / Twitter | BM | EDU | Friday fusion fact | PLANNED
40 | 2026-07-24 | Friday | Instagram | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
41 | 2026-07-25 | Saturday | X / Twitter | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
43 | 2026-07-27 | Monday | LinkedIn Company | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
43 | 2026-07-27 | Monday | LinkedIn — Nelson | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
43 | 2026-07-27 | Monday | X / Twitter | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
43 | 2026-07-27 | Monday | X / Twitter | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
43 | 2026-07-27 | Monday | Instagram | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
44 | 2026-07-28 | Tuesday | LinkedIn — Reid | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
44 | 2026-07-28 | Tuesday | X / Twitter | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
44 | 2026-07-28 | Tuesday | X / Twitter | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
45 | 2026-07-29 | Wednesday | LinkedIn Company | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
45 | 2026-07-29 | Wednesday | LinkedIn — Nelson | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
45 | 2026-07-29 | Wednesday | X / Twitter | BM | AI | Hyperscaler capex commentary | PLANNED
45 | 2026-07-29 | Wednesday | X / Twitter | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
45 | 2026-07-29 | Wednesday | Instagram | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
46 | 2026-07-30 | Thursday | LinkedIn Company | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
46 | 2026-07-30 | Thursday | LinkedIn — Hawkins | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
46 | 2026-07-30 | Thursday | X / Twitter | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
46 | 2026-07-30 | Thursday | X / Twitter | BM | EDU | What is helium-3? Where does it come from? | PLANNED
47 | 2026-07-31 | Friday | LinkedIn Company | BM | FV | Friday: a single sharp thought from the team | PLANNED
47 | 2026-07-31 | Friday | LinkedIn — Nelson | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
47 | 2026-07-31 | Friday | X / Twitter | BM | BIP | Photo + caption: shop floor / control room | PLANNED
47 | 2026-07-31 | Friday | X / Twitter | BM | EDU | Friday fusion fact | PLANNED
47 | 2026-07-31 | Friday | Instagram | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
48 | 2026-08-01 | Saturday | X / Twitter | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
48 | 2026-08-01 | Saturday | Newsletter | BM | IR/DEF | Bi-monthly send: State of Fusion + Reid Procurement Note + Texatron progress | PLANNED | LEGAL review on any milestone references
50 | 2026-08-03 | Monday | LinkedIn Company | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
50 | 2026-08-03 | Monday | LinkedIn — Nelson | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
50 | 2026-08-03 | Monday | X / Twitter | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
50 | 2026-08-03 | Monday | X / Twitter | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
50 | 2026-08-03 | Monday | Instagram | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
51 | 2026-08-04 | Tuesday | LinkedIn — Reid | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
51 | 2026-08-04 | Tuesday | X / Twitter | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
51 | 2026-08-04 | Tuesday | X / Twitter | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
52 | 2026-08-05 | Wednesday | LinkedIn Company | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
52 | 2026-08-05 | Wednesday | LinkedIn — Nelson | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
52 | 2026-08-05 | Wednesday | X / Twitter | BM | AI | Hyperscaler capex commentary | PLANNED
52 | 2026-08-05 | Wednesday | X / Twitter | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
52 | 2026-08-05 | Wednesday | Instagram | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
53 | 2026-08-06 | Thursday | LinkedIn Company | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
53 | 2026-08-06 | Thursday | LinkedIn — Hawkins | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
53 | 2026-08-06 | Thursday | X / Twitter | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
53 | 2026-08-06 | Thursday | X / Twitter | BM | EDU | What is helium-3? Where does it come from? | PLANNED
54 | 2026-08-07 | Friday | LinkedIn Company | BM | FV | Friday: a single sharp thought from the team | PLANNED
54 | 2026-08-07 | Friday | LinkedIn — Nelson | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
54 | 2026-08-07 | Friday | X / Twitter | BM | BIP | Photo + caption: shop floor / control room | PLANNED
54 | 2026-08-07 | Friday | X / Twitter | BM | EDU | Friday fusion fact | PLANNED
54 | 2026-08-07 | Friday | Instagram | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
55 | 2026-08-08 | Saturday | X / Twitter | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
57 | 2026-08-10 | Monday | LinkedIn Company | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
57 | 2026-08-10 | Monday | LinkedIn — Nelson | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
57 | 2026-08-10 | Monday | X / Twitter | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
57 | 2026-08-10 | Monday | X / Twitter | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
57 | 2026-08-10 | Monday | Instagram | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
58 | 2026-08-11 | Tuesday | LinkedIn — Reid | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
58 | 2026-08-11 | Tuesday | X / Twitter | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
58 | 2026-08-11 | Tuesday | X / Twitter | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
59 | 2026-08-12 | Wednesday | LinkedIn Company | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
59 | 2026-08-12 | Wednesday | LinkedIn — Nelson | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
59 | 2026-08-12 | Wednesday | X / Twitter | BM | AI | Hyperscaler capex commentary | PLANNED
59 | 2026-08-12 | Wednesday | X / Twitter | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
59 | 2026-08-12 | Wednesday | Instagram | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
59 | 2026-08-12 | Wednesday | YouTube | BM/Nelson | BIP/EDU | CEO Update — what we shipped this month | PLANNED
60 | 2026-08-13 | Thursday | LinkedIn Company | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
60 | 2026-08-13 | Thursday | LinkedIn — Hawkins | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
60 | 2026-08-13 | Thursday | X / Twitter | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
60 | 2026-08-13 | Thursday | X / Twitter | BM | EDU | What is helium-3? Where does it come from? | PLANNED
61 | 2026-08-14 | Friday | LinkedIn Company | BM | FV | Friday: a single sharp thought from the team | PLANNED
61 | 2026-08-14 | Friday | LinkedIn — Nelson | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
61 | 2026-08-14 | Friday | X / Twitter | BM | BIP | Photo + caption: shop floor / control room | PLANNED
61 | 2026-08-14 | Friday | X / Twitter | BM | EDU | Friday fusion fact | PLANNED
61 | 2026-08-14 | Friday | Instagram | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
62 | 2026-08-15 | Saturday | X / Twitter | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
62 | 2026-08-15 | Saturday | Newsletter | BM | IR/DEF | Bi-monthly send: State of Fusion + Reid Procurement Note + Texatron progress | PLANNED | LEGAL review on any milestone references
64 | 2026-08-17 | Monday | LinkedIn Company | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
64 | 2026-08-17 | Monday | LinkedIn — Nelson | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
64 | 2026-08-17 | Monday | X / Twitter | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
64 | 2026-08-17 | Monday | X / Twitter | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
64 | 2026-08-17 | Monday | Instagram | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
65 | 2026-08-18 | Tuesday | LinkedIn — Reid | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
65 | 2026-08-18 | Tuesday | X / Twitter | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
65 | 2026-08-18 | Tuesday | X / Twitter | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
66 | 2026-08-19 | Wednesday | LinkedIn Company | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
66 | 2026-08-19 | Wednesday | LinkedIn — Nelson | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
66 | 2026-08-19 | Wednesday | X / Twitter | BM | AI | Hyperscaler capex commentary | PLANNED
66 | 2026-08-19 | Wednesday | X / Twitter | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
66 | 2026-08-19 | Wednesday | Instagram | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
67 | 2026-08-20 | Thursday | LinkedIn Company | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
67 | 2026-08-20 | Thursday | LinkedIn — Hawkins | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
67 | 2026-08-20 | Thursday | X / Twitter | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
67 | 2026-08-20 | Thursday | X / Twitter | BM | EDU | What is helium-3? Where does it come from? | PLANNED
68 | 2026-08-21 | Friday | LinkedIn Company | BM | FV | Friday: a single sharp thought from the team | PLANNED
68 | 2026-08-21 | Friday | LinkedIn — Nelson | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
68 | 2026-08-21 | Friday | X / Twitter | BM | BIP | Photo + caption: shop floor / control room | PLANNED
68 | 2026-08-21 | Friday | X / Twitter | BM | EDU | Friday fusion fact | PLANNED
68 | 2026-08-21 | Friday | Instagram | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
69 | 2026-08-22 | Saturday | X / Twitter | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
71 | 2026-08-24 | Monday | LinkedIn Company | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
71 | 2026-08-24 | Monday | LinkedIn — Nelson | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
71 | 2026-08-24 | Monday | X / Twitter | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
71 | 2026-08-24 | Monday | X / Twitter | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
71 | 2026-08-24 | Monday | Instagram | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
72 | 2026-08-25 | Tuesday | LinkedIn — Reid | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
72 | 2026-08-25 | Tuesday | X / Twitter | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
72 | 2026-08-25 | Tuesday | X / Twitter | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
73 | 2026-08-26 | Wednesday | LinkedIn Company | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
73 | 2026-08-26 | Wednesday | LinkedIn — Nelson | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
73 | 2026-08-26 | Wednesday | X / Twitter | BM | AI | Hyperscaler capex commentary | PLANNED
73 | 2026-08-26 | Wednesday | X / Twitter | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
73 | 2026-08-26 | Wednesday | Instagram | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
73 | 2026-08-26 | Wednesday | YouTube | BM/Nelson | BIP/EDU | Technology Deep-Dive — aneutronic fundamentals series | PLANNED
74 | 2026-08-27 | Thursday | LinkedIn Company | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
74 | 2026-08-27 | Thursday | LinkedIn — Hawkins | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
74 | 2026-08-27 | Thursday | X / Twitter | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
74 | 2026-08-27 | Thursday | X / Twitter | BM | EDU | What is helium-3? Where does it come from? | PLANNED
75 | 2026-08-28 | Friday | LinkedIn Company | BM | FV | Friday: a single sharp thought from the team | PLANNED
75 | 2026-08-28 | Friday | LinkedIn — Nelson | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
75 | 2026-08-28 | Friday | X / Twitter | BM | BIP | Photo + caption: shop floor / control room | PLANNED
75 | 2026-08-28 | Friday | X / Twitter | BM | EDU | Friday fusion fact | PLANNED
75 | 2026-08-28 | Friday | Instagram | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
76 | 2026-08-29 | Saturday | X / Twitter | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
78 | 2026-08-31 | Monday | LinkedIn Company | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
78 | 2026-08-31 | Monday | LinkedIn — Nelson | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
78 | 2026-08-31 | Monday | X / Twitter | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
78 | 2026-08-31 | Monday | X / Twitter | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
78 | 2026-08-31 | Monday | Instagram | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
79 | 2026-09-01 | Tuesday | LinkedIn — Reid | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
79 | 2026-09-01 | Tuesday | X / Twitter | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
79 | 2026-09-01 | Tuesday | X / Twitter | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
79 | 2026-09-01 | Tuesday | Newsletter | BM | IR/DEF | Bi-monthly send: State of Fusion + Reid Procurement Note + Texatron progress | PLANNED | LEGAL review on any milestone references
80 | 2026-09-02 | Wednesday | LinkedIn Company | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
80 | 2026-09-02 | Wednesday | LinkedIn — Nelson | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
80 | 2026-09-02 | Wednesday | X / Twitter | BM | AI | Hyperscaler capex commentary | PLANNED
80 | 2026-09-02 | Wednesday | X / Twitter | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
80 | 2026-09-02 | Wednesday | Instagram | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
81 | 2026-09-03 | Thursday | LinkedIn Company | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
81 | 2026-09-03 | Thursday | LinkedIn — Hawkins | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
81 | 2026-09-03 | Thursday | X / Twitter | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
81 | 2026-09-03 | Thursday | X / Twitter | BM | EDU | What is helium-3? Where does it come from? | PLANNED
82 | 2026-09-04 | Friday | LinkedIn Company | BM | FV | Friday: a single sharp thought from the team | PLANNED
82 | 2026-09-04 | Friday | LinkedIn — Nelson | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
82 | 2026-09-04 | Friday | X / Twitter | BM | BIP | Photo + caption: shop floor / control room | PLANNED
82 | 2026-09-04 | Friday | X / Twitter | BM | EDU | Friday fusion fact | PLANNED
82 | 2026-09-04 | Friday | Instagram | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
83 | 2026-09-05 | Saturday | X / Twitter | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
85 | 2026-09-07 | Monday | LinkedIn Company | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
85 | 2026-09-07 | Monday | LinkedIn — Nelson | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
85 | 2026-09-07 | Monday | X / Twitter | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
85 | 2026-09-07 | Monday | X / Twitter | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
85 | 2026-09-07 | Monday | Instagram | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
86 | 2026-09-08 | Tuesday | LinkedIn — Reid | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
86 | 2026-09-08 | Tuesday | X / Twitter | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
86 | 2026-09-08 | Tuesday | X / Twitter | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
87 | 2026-09-09 | Wednesday | LinkedIn Company | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
87 | 2026-09-09 | Wednesday | LinkedIn — Nelson | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
87 | 2026-09-09 | Wednesday | X / Twitter | BM | AI | Hyperscaler capex commentary | PLANNED
87 | 2026-09-09 | Wednesday | X / Twitter | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
87 | 2026-09-09 | Wednesday | Instagram | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
87 | 2026-09-09 | Wednesday | YouTube | BM/Nelson | BIP/EDU | CEO Update — what we shipped this month | PLANNED
88 | 2026-09-10 | Thursday | LinkedIn Company | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
88 | 2026-09-10 | Thursday | LinkedIn — Hawkins | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
88 | 2026-09-10 | Thursday | X / Twitter | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
88 | 2026-09-10 | Thursday | X / Twitter | BM | EDU | What is helium-3? Where does it come from? | PLANNED
89 | 2026-09-11 | Friday | LinkedIn Company | BM | FV | Friday: a single sharp thought from the team | PLANNED
89 | 2026-09-11 | Friday | LinkedIn — Nelson | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
89 | 2026-09-11 | Friday | X / Twitter | BM | BIP | Photo + caption: shop floor / control room | PLANNED
89 | 2026-09-11 | Friday | X / Twitter | BM | EDU | Friday fusion fact | PLANNED
89 | 2026-09-11 | Friday | Instagram | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
90 | 2026-09-12 | Saturday | X / Twitter | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
TOTAL CONTENT PIECES (90 DAYS) | [5 empty] | 311

## LinkedIn Company
Day | Date | Day of Week | Owner | Pillar | Working Title / Hook | Status
1 | 2026-06-15 | Monday | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
3 | 2026-06-17 | Wednesday | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
4 | 2026-06-18 | Thursday | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
5 | 2026-06-19 | Friday | BM | FV | Friday: a single sharp thought from the team | PLANNED
8 | 2026-06-22 | Monday | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
10 | 2026-06-24 | Wednesday | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
11 | 2026-06-25 | Thursday | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
12 | 2026-06-26 | Friday | BM | FV | Friday: a single sharp thought from the team | PLANNED
15 | 2026-06-29 | Monday | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
17 | 2026-07-01 | Wednesday | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
18 | 2026-07-02 | Thursday | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
19 | 2026-07-03 | Friday | BM | FV | Friday: a single sharp thought from the team | PLANNED
22 | 2026-07-06 | Monday | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
24 | 2026-07-08 | Wednesday | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
25 | 2026-07-09 | Thursday | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
26 | 2026-07-10 | Friday | BM | FV | Friday: a single sharp thought from the team | PLANNED
29 | 2026-07-13 | Monday | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
31 | 2026-07-15 | Wednesday | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
32 | 2026-07-16 | Thursday | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
33 | 2026-07-17 | Friday | BM | FV | Friday: a single sharp thought from the team | PLANNED
36 | 2026-07-20 | Monday | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
38 | 2026-07-22 | Wednesday | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
39 | 2026-07-23 | Thursday | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
40 | 2026-07-24 | Friday | BM | FV | Friday: a single sharp thought from the team | PLANNED
43 | 2026-07-27 | Monday | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
45 | 2026-07-29 | Wednesday | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
46 | 2026-07-30 | Thursday | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
47 | 2026-07-31 | Friday | BM | FV | Friday: a single sharp thought from the team | PLANNED
50 | 2026-08-03 | Monday | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
52 | 2026-08-05 | Wednesday | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
53 | 2026-08-06 | Thursday | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
54 | 2026-08-07 | Friday | BM | FV | Friday: a single sharp thought from the team | PLANNED
57 | 2026-08-10 | Monday | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
59 | 2026-08-12 | Wednesday | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
60 | 2026-08-13 | Thursday | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
61 | 2026-08-14 | Friday | BM | FV | Friday: a single sharp thought from the team | PLANNED
64 | 2026-08-17 | Monday | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
66 | 2026-08-19 | Wednesday | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
67 | 2026-08-20 | Thursday | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
68 | 2026-08-21 | Friday | BM | FV | Friday: a single sharp thought from the team | PLANNED
71 | 2026-08-24 | Monday | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
73 | 2026-08-26 | Wednesday | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
74 | 2026-08-27 | Thursday | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
75 | 2026-08-28 | Friday | BM | FV | Friday: a single sharp thought from the team | PLANNED
78 | 2026-08-31 | Monday | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
80 | 2026-09-02 | Wednesday | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
81 | 2026-09-03 | Thursday | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
82 | 2026-09-04 | Friday | BM | FV | Friday: a single sharp thought from the team | PLANNED
85 | 2026-09-07 | Monday | BM | BIP | Week-in-review: Texatron build progress, what we shipped | PLANNED
87 | 2026-09-09 | Wednesday | BM | AI | Long-form: aneutronic fusion and AI baseload (anchored to IEA) | PLANNED
88 | 2026-09-10 | Thursday | BM | IR | Milestone update or quiet-period-compatible progress note | PLANNED
89 | 2026-09-11 | Friday | BM | FV | Friday: a single sharp thought from the team | PLANNED

## Executive Posts
Day | Date | Day of Week | Owner | Pillar | Working Title / Hook | Status
1 | 2026-06-15 | Monday | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
2 | 2026-06-16 | Tuesday | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
3 | 2026-06-17 | Wednesday | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
4 | 2026-06-18 | Thursday | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
5 | 2026-06-19 | Friday | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
8 | 2026-06-22 | Monday | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
9 | 2026-06-23 | Tuesday | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
10 | 2026-06-24 | Wednesday | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
11 | 2026-06-25 | Thursday | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
12 | 2026-06-26 | Friday | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
15 | 2026-06-29 | Monday | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
16 | 2026-06-30 | Tuesday | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
17 | 2026-07-01 | Wednesday | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
18 | 2026-07-02 | Thursday | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
19 | 2026-07-03 | Friday | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
22 | 2026-07-06 | Monday | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
23 | 2026-07-07 | Tuesday | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
24 | 2026-07-08 | Wednesday | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
25 | 2026-07-09 | Thursday | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
26 | 2026-07-10 | Friday | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
29 | 2026-07-13 | Monday | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
30 | 2026-07-14 | Tuesday | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
31 | 2026-07-15 | Wednesday | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
32 | 2026-07-16 | Thursday | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
33 | 2026-07-17 | Friday | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
36 | 2026-07-20 | Monday | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
37 | 2026-07-21 | Tuesday | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
38 | 2026-07-22 | Wednesday | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
39 | 2026-07-23 | Thursday | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
40 | 2026-07-24 | Friday | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
43 | 2026-07-27 | Monday | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
44 | 2026-07-28 | Tuesday | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
45 | 2026-07-29 | Wednesday | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
46 | 2026-07-30 | Thursday | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
47 | 2026-07-31 | Friday | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
50 | 2026-08-03 | Monday | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
51 | 2026-08-04 | Tuesday | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
52 | 2026-08-05 | Wednesday | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
53 | 2026-08-06 | Thursday | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
54 | 2026-08-07 | Friday | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
57 | 2026-08-10 | Monday | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
58 | 2026-08-11 | Tuesday | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
59 | 2026-08-12 | Wednesday | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
60 | 2026-08-13 | Thursday | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
61 | 2026-08-14 | Friday | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
64 | 2026-08-17 | Monday | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
65 | 2026-08-18 | Tuesday | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
66 | 2026-08-19 | Wednesday | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
67 | 2026-08-20 | Thursday | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
68 | 2026-08-21 | Friday | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
71 | 2026-08-24 | Monday | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
72 | 2026-08-25 | Tuesday | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
73 | 2026-08-26 | Wednesday | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
74 | 2026-08-27 | Thursday | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
75 | 2026-08-28 | Friday | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
78 | 2026-08-31 | Monday | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
79 | 2026-09-01 | Tuesday | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
80 | 2026-09-02 | Wednesday | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
81 | 2026-09-03 | Thursday | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
82 | 2026-09-04 | Friday | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED
85 | 2026-09-07 | Monday | BM/Nelson | BIP | Engineering note: a specific decision the team made this week | PLANNED
86 | 2026-09-08 | Tuesday | BM/Reid | DEF | Procurement note: EO 14299 / ANPI / Janus context for the week | PLANNED
87 | 2026-09-09 | Wednesday | BM/Nelson | EDU | Carousel: how direct energy conversion works | PLANNED
88 | 2026-09-10 | Thursday | BM/Hawkins | IR | Capital markets note (LEGAL review) | PLANNED
89 | 2026-09-11 | Friday | BM/Nelson | FV | End-of-week reflection: what we learned | PLANNED

## X Twitter
Day | Date | Day of Week | Owner | Pillar | Working Title / Hook | Status
1 | 2026-06-15 | Monday | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
1 | 2026-06-15 | Monday | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
2 | 2026-06-16 | Tuesday | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
2 | 2026-06-16 | Tuesday | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
3 | 2026-06-17 | Wednesday | BM | AI | Hyperscaler capex commentary | PLANNED
3 | 2026-06-17 | Wednesday | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
4 | 2026-06-18 | Thursday | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
4 | 2026-06-18 | Thursday | BM | EDU | What is helium-3? Where does it come from? | PLANNED
5 | 2026-06-19 | Friday | BM | BIP | Photo + caption: shop floor / control room | PLANNED
5 | 2026-06-19 | Friday | BM | EDU | Friday fusion fact | PLANNED
6 | 2026-06-20 | Saturday | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
8 | 2026-06-22 | Monday | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
8 | 2026-06-22 | Monday | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
9 | 2026-06-23 | Tuesday | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
9 | 2026-06-23 | Tuesday | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
10 | 2026-06-24 | Wednesday | BM | AI | Hyperscaler capex commentary | PLANNED
10 | 2026-06-24 | Wednesday | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
11 | 2026-06-25 | Thursday | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
11 | 2026-06-25 | Thursday | BM | EDU | What is helium-3? Where does it come from? | PLANNED
12 | 2026-06-26 | Friday | BM | BIP | Photo + caption: shop floor / control room | PLANNED
12 | 2026-06-26 | Friday | BM | EDU | Friday fusion fact | PLANNED
13 | 2026-06-27 | Saturday | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
15 | 2026-06-29 | Monday | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
15 | 2026-06-29 | Monday | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
16 | 2026-06-30 | Tuesday | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
16 | 2026-06-30 | Tuesday | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
17 | 2026-07-01 | Wednesday | BM | AI | Hyperscaler capex commentary | PLANNED
17 | 2026-07-01 | Wednesday | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
18 | 2026-07-02 | Thursday | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
18 | 2026-07-02 | Thursday | BM | EDU | What is helium-3? Where does it come from? | PLANNED
19 | 2026-07-03 | Friday | BM | BIP | Photo + caption: shop floor / control room | PLANNED
19 | 2026-07-03 | Friday | BM | EDU | Friday fusion fact | PLANNED
20 | 2026-07-04 | Saturday | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
22 | 2026-07-06 | Monday | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
22 | 2026-07-06 | Monday | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
23 | 2026-07-07 | Tuesday | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
23 | 2026-07-07 | Tuesday | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
24 | 2026-07-08 | Wednesday | BM | AI | Hyperscaler capex commentary | PLANNED
24 | 2026-07-08 | Wednesday | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
25 | 2026-07-09 | Thursday | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
25 | 2026-07-09 | Thursday | BM | EDU | What is helium-3? Where does it come from? | PLANNED
26 | 2026-07-10 | Friday | BM | BIP | Photo + caption: shop floor / control room | PLANNED
26 | 2026-07-10 | Friday | BM | EDU | Friday fusion fact | PLANNED
27 | 2026-07-11 | Saturday | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
29 | 2026-07-13 | Monday | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
29 | 2026-07-13 | Monday | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
30 | 2026-07-14 | Tuesday | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
30 | 2026-07-14 | Tuesday | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
31 | 2026-07-15 | Wednesday | BM | AI | Hyperscaler capex commentary | PLANNED
31 | 2026-07-15 | Wednesday | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
32 | 2026-07-16 | Thursday | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
32 | 2026-07-16 | Thursday | BM | EDU | What is helium-3? Where does it come from? | PLANNED
33 | 2026-07-17 | Friday | BM | BIP | Photo + caption: shop floor / control room | PLANNED
33 | 2026-07-17 | Friday | BM | EDU | Friday fusion fact | PLANNED
34 | 2026-07-18 | Saturday | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
36 | 2026-07-20 | Monday | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
36 | 2026-07-20 | Monday | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
37 | 2026-07-21 | Tuesday | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
37 | 2026-07-21 | Tuesday | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
38 | 2026-07-22 | Wednesday | BM | AI | Hyperscaler capex commentary | PLANNED
38 | 2026-07-22 | Wednesday | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
39 | 2026-07-23 | Thursday | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
39 | 2026-07-23 | Thursday | BM | EDU | What is helium-3? Where does it come from? | PLANNED
40 | 2026-07-24 | Friday | BM | BIP | Photo + caption: shop floor / control room | PLANNED
40 | 2026-07-24 | Friday | BM | EDU | Friday fusion fact | PLANNED
41 | 2026-07-25 | Saturday | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
43 | 2026-07-27 | Monday | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
43 | 2026-07-27 | Monday | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
44 | 2026-07-28 | Tuesday | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
44 | 2026-07-28 | Tuesday | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
45 | 2026-07-29 | Wednesday | BM | AI | Hyperscaler capex commentary | PLANNED
45 | 2026-07-29 | Wednesday | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
46 | 2026-07-30 | Thursday | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
46 | 2026-07-30 | Thursday | BM | EDU | What is helium-3? Where does it come from? | PLANNED
47 | 2026-07-31 | Friday | BM | BIP | Photo + caption: shop floor / control room | PLANNED
47 | 2026-07-31 | Friday | BM | EDU | Friday fusion fact | PLANNED
48 | 2026-08-01 | Saturday | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
50 | 2026-08-03 | Monday | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
50 | 2026-08-03 | Monday | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
51 | 2026-08-04 | Tuesday | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
51 | 2026-08-04 | Tuesday | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
52 | 2026-08-05 | Wednesday | BM | AI | Hyperscaler capex commentary | PLANNED
52 | 2026-08-05 | Wednesday | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
53 | 2026-08-06 | Thursday | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
53 | 2026-08-06 | Thursday | BM | EDU | What is helium-3? Where does it come from? | PLANNED
54 | 2026-08-07 | Friday | BM | BIP | Photo + caption: shop floor / control room | PLANNED
54 | 2026-08-07 | Friday | BM | EDU | Friday fusion fact | PLANNED
55 | 2026-08-08 | Saturday | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
57 | 2026-08-10 | Monday | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
57 | 2026-08-10 | Monday | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
58 | 2026-08-11 | Tuesday | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
58 | 2026-08-11 | Tuesday | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
59 | 2026-08-12 | Wednesday | BM | AI | Hyperscaler capex commentary | PLANNED
59 | 2026-08-12 | Wednesday | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
60 | 2026-08-13 | Thursday | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
60 | 2026-08-13 | Thursday | BM | EDU | What is helium-3? Where does it come from? | PLANNED
61 | 2026-08-14 | Friday | BM | BIP | Photo + caption: shop floor / control room | PLANNED
61 | 2026-08-14 | Friday | BM | EDU | Friday fusion fact | PLANNED
62 | 2026-08-15 | Saturday | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
64 | 2026-08-17 | Monday | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
64 | 2026-08-17 | Monday | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
65 | 2026-08-18 | Tuesday | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
65 | 2026-08-18 | Tuesday | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
66 | 2026-08-19 | Wednesday | BM | AI | Hyperscaler capex commentary | PLANNED
66 | 2026-08-19 | Wednesday | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
67 | 2026-08-20 | Thursday | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
67 | 2026-08-20 | Thursday | BM | EDU | What is helium-3? Where does it come from? | PLANNED
68 | 2026-08-21 | Friday | BM | BIP | Photo + caption: shop floor / control room | PLANNED
68 | 2026-08-21 | Friday | BM | EDU | Friday fusion fact | PLANNED
69 | 2026-08-22 | Saturday | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
71 | 2026-08-24 | Monday | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
71 | 2026-08-24 | Monday | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
72 | 2026-08-25 | Tuesday | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
72 | 2026-08-25 | Tuesday | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
73 | 2026-08-26 | Wednesday | BM | AI | Hyperscaler capex commentary | PLANNED
73 | 2026-08-26 | Wednesday | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
74 | 2026-08-27 | Thursday | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
74 | 2026-08-27 | Thursday | BM | EDU | What is helium-3? Where does it come from? | PLANNED
75 | 2026-08-28 | Friday | BM | BIP | Photo + caption: shop floor / control room | PLANNED
75 | 2026-08-28 | Friday | BM | EDU | Friday fusion fact | PLANNED
76 | 2026-08-29 | Saturday | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
78 | 2026-08-31 | Monday | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
78 | 2026-08-31 | Monday | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
79 | 2026-09-01 | Tuesday | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
79 | 2026-09-01 | Tuesday | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
80 | 2026-09-02 | Wednesday | BM | AI | Hyperscaler capex commentary | PLANNED
80 | 2026-09-02 | Wednesday | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
81 | 2026-09-03 | Thursday | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
81 | 2026-09-03 | Thursday | BM | EDU | What is helium-3? Where does it come from? | PLANNED
82 | 2026-09-04 | Friday | BM | BIP | Photo + caption: shop floor / control room | PLANNED
82 | 2026-09-04 | Friday | BM | EDU | Friday fusion fact | PLANNED
83 | 2026-09-05 | Saturday | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED
85 | 2026-09-07 | Monday | BM | EDU | Aneutronic fusion explainer thread (1/5) | PLANNED
85 | 2026-09-07 | Monday | BM | BIP | Photo: Texatron diagnostics close-up | PLANNED
86 | 2026-09-08 | Tuesday | BM | DEF | Quote-tweet defense-energy news with AMFN POV | PLANNED
86 | 2026-09-08 | Tuesday | BM | AI | Stat post: IEA data center demand snapshot | PLANNED
87 | 2026-09-09 | Wednesday | BM | AI | Hyperscaler capex commentary | PLANNED
87 | 2026-09-09 | Wednesday | BM | FV | Reply / engage on a peer fusion-industry post | PLANNED
88 | 2026-09-10 | Thursday | BM | BIP | Thread: this week's engineering wins (3-5 posts) | PLANNED
88 | 2026-09-10 | Thursday | BM | EDU | What is helium-3? Where does it come from? | PLANNED
89 | 2026-09-11 | Friday | BM | BIP | Photo + caption: shop floor / control room | PLANNED
89 | 2026-09-11 | Friday | BM | EDU | Friday fusion fact | PLANNED
90 | 2026-09-12 | Saturday | BM | EDU | Weekend long-form quote-tweet of an industry article | PLANNED

## Instagram
Day | Date | Day of Week | Owner | Pillar | Working Title / Hook | Status
1 | 2026-06-15 | Monday | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
3 | 2026-06-17 | Wednesday | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
5 | 2026-06-19 | Friday | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
8 | 2026-06-22 | Monday | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
10 | 2026-06-24 | Wednesday | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
12 | 2026-06-26 | Friday | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
15 | 2026-06-29 | Monday | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
17 | 2026-07-01 | Wednesday | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
19 | 2026-07-03 | Friday | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
22 | 2026-07-06 | Monday | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
24 | 2026-07-08 | Wednesday | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
26 | 2026-07-10 | Friday | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
29 | 2026-07-13 | Monday | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
31 | 2026-07-15 | Wednesday | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
33 | 2026-07-17 | Friday | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
36 | 2026-07-20 | Monday | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
38 | 2026-07-22 | Wednesday | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
40 | 2026-07-24 | Friday | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
43 | 2026-07-27 | Monday | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
45 | 2026-07-29 | Wednesday | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
47 | 2026-07-31 | Friday | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
50 | 2026-08-03 | Monday | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
52 | 2026-08-05 | Wednesday | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
54 | 2026-08-07 | Friday | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
57 | 2026-08-10 | Monday | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
59 | 2026-08-12 | Wednesday | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
61 | 2026-08-14 | Friday | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
64 | 2026-08-17 | Monday | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
66 | 2026-08-19 | Wednesday | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
68 | 2026-08-21 | Friday | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
71 | 2026-08-24 | Monday | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
73 | 2026-08-26 | Wednesday | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
75 | 2026-08-28 | Friday | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
78 | 2026-08-31 | Monday | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
80 | 2026-09-02 | Wednesday | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
82 | 2026-09-04 | Friday | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED
85 | 2026-09-07 | Monday | BM | BIP | Visual: lab shot, caption tells the story behind it | PLANNED
87 | 2026-09-09 | Wednesday | BM | EDU | Infographic: D–He-3 vs D–T trade-offs | PLANNED
89 | 2026-09-11 | Friday | BM | FV | Team Friday: a hire, a moment, a small win | PLANNED

## YouTube & Newsletter
Month | Date | Channel | Format | Working Title | Owner | Status | Notes
Month 1 | 2026-06-15 | Newsletter | Bi-monthly send | Issue 01: 'Why we're publishing — and what to expect' | BM/Hawkins | PLANNED | Welcome issue; sets cadence
Month 1 | 2026-06-24 | YouTube | Long-form: CEO Update | Texatron build month 1: what we shipped | BM/Nelson | PLANNED | Shot in lab; 5–8 min
Month 1 | 2026-07-01 | Newsletter | Bi-monthly send | Issue 02: Texatron progress + Reid Procurement Note debut | BM/Reid/Hawkins | PLANNED | LEGAL review on milestone refs
Month 1 | 2026-07-08 | YouTube | Long-form: Tech Deep-Dive | Aneutronic fusion 101: why D–He-3 | BM/Nelson | PLANNED | Whiteboard explainer style
Month 2 | 2026-07-15 | Newsletter | Bi-monthly send | Issue 03: AI energy + Texatron diagnostics integration | BM/Hawkins | PLANNED
Month 2 | 2026-07-22 | YouTube | Long-form: CEO Update | Texatron build month 2: diagnostics suite | BM/Nelson | PLANNED
Month 2 | 2026-08-01 | Newsletter | Bi-monthly send | Issue 04: Defense procurement focus (Reid lead) | BM/Reid | PLANNED
Month 2 | 2026-08-12 | YouTube | Long-form: Tech Deep-Dive | How direct energy conversion works | BM/Nelson | PLANNED
Month 3 | 2026-08-15 | Newsletter | Bi-monthly send | Issue 05: Helium-3 supply chain transparency | BM/Hawkins | PLANNED | Coordinate with corporate counsel on disclosures
Month 3 | 2026-08-26 | YouTube | Long-form: CEO Update | Texatron build month 3: independent test prep | BM/Nelson | PLANNED
Month 3 | 2026-09-01 | Newsletter | Bi-monthly send | Issue 06: 90-day review + what's next | BM/Hawkins | PLANNED | Phase 1 close-out
Month 3 | 2026-09-09 | YouTube | Long-form: Tech Deep-Dive | Aneutronic vs D–T: the honest trade-offs | BM/Nelson | PLANNED